## Template
Level | Name | Description | Project Type | Project Manager | Extension | Ext Deadline Increment | Ext Deadline Amount | Ext Static Deadline | Is Extendable | Project Frequency | Web Collection | Priority | Is Month End | Start Date Increment | Start Date Amount | Start Static Date
Project | Termination | Termination with Data Collection | Distribution | Distribution Specialist | FALSE | D | 6 |  | FALSE | Non-Recurring | TRUE | Normal | FALSE | None
Level | Name\Question | Time Code | Days To Complete | Role Assigned | Review Step | DataType | Required | Project Field | Show on Project | Show on Plan | Worktray | Event | Task Category
Task Grouping | Data Collection
Task | Distribution Request Notification | 999 | 0 | Distribution Specialist | FALSE | [5 empty] | Distribution
Task Item | An electronic Data Collection email needs to be sent to the client alerting them that the process for collecting their information using PlanSponsorLink.com is available. This process can be done using the Blast Email tools under the Communication menu. You can also manually send an email to alert the client. |  |  |  |  | None | FALSE
Task | Approval and Submission | 999 | 0 | Unassigned | FALSE | [5 empty] | Distribution
Task Item | This task will be completed by your client using PlanSponsorLink.com. When they have completed and approved the data for this Task, the Task will show as completed here and on the Task Grouping tab. To see the details of the information your client has entered/approved, click on the Data Collection button on the header bar. |  |  |  |  | None | FALSE
Task Grouping | Preliminary Information
Task | Document Specifications Verification | 101 | 1 | Distribution Specialist | FALSE | [5 empty] | Distribution
Task Item | Has it been verified that this is an allowable distribution per the Plan Document? |  |  |  |  | Yes/No | TRUE
Task Item | Does the document provide for Mandatory Cash out without participant election? |  |  |  |  | Yes/No | TRUE
Task Item | If yes, are rollovers excluded from vested account balance determination for mandatory cash-out? |  |  |  |  | Yes/No | FALSE
Task Item | Obtain vesting schedules from the Plan Document for each applicable account source. |  |  |  |  | Yes/No | TRUE
Task | Review Preliminary Data | 101 | 1 | Distribution Specialist | TRUE | [5 empty] | Distribution
Task Item | Review participant Data is entered correctly |  |  |  |  | Checkbox | TRUE
Task Item | Check that the participant distribution information is correct |  |  |  |  | Checkbox | TRUE
Task Item | Verify that the request is an allowable distribution |  |  |  |  | Checkbox | TRUE
Task Item | Check the vesting schedule for the different sources |  |  |  |  | Checkbox | TRUE
Task Grouping | Termination of Employment Distribution
Task | Termination Distribution Data | 101 | 1 | Distribution Specialist | FALSE | [5 empty] | Distribution
Task Item | Does the participant have any outstanding loans? |  |  |  |  | Yes/No | FALSE
Task Item | If yes, enter amount |  |  |  |  | Text | FALSE
Task Item | Determine the participant's vested account balance |  |  |  |  | Text | TRUE
Task Item | Is participant's vested account balance less than $5000? |  |  |  |  | Yes/No | TRUE
Task Item | If yes, is this a Mandatory Cash-out without participant election |  |  |  |  | Yes/No | FALSE
Task Item | If participant < age 59 1/2, does excise tax apply? |  |  |  |  | Yes/No | TRUE
Task Item | Calculate excise tax, if applicable |  |  |  |  | Text | FALSE
Task Item | Calculate withholding tax, if applicaable |  |  |  |  | Text | FALSE
Task | Paperwork | 101 | 1 | Distribution Specialist | FALSE | [5 empty] | Distribution
Task Item | Is spousal consent required? |  |  |  |  | Yes/No | TRUE
Task Item | Spousal request form received, if applicable |  |  |  |  | Date | FALSE
Task Item | Is the paperwork in good order? |  |  |  |  | Yes/Not in good order | TRUE
Task Item | If paperwork not in good order, client contacted regarding missing information |  |  |  |  | Date | FALSE
Task Item | Verify that all necessary paperwork is completed and signed |  |  |  |  | Date | TRUE
Task Item | Put distribution file together for review - make sure to include all necessary documentation |  |  |  |  | Date | TRUE
Task | Review Termination Distribution Data | 101 | 1 | Reviewer | TRUE | [5 empty] | Distribution
Task Item | Check for outstanding loans |  |  |  |  | Checkbox | TRUE
Task Item | Check if spousal consent is needed and if so it's on file |  |  |  |  | Checkbox | TRUE
Task Item | Were the correct withholding amounts calculated if applicable |  |  |  |  | Checkbox | TRUE
Task Item | Verify that all paperwork is in good order |  |  |  |  | Checkbox | TRUE
Task Grouping | Submit Paperwork
Task | Information submitted | 101 | 0 | Distribution Specialist | FALSE | [5 empty] | Distribution
Task Item | Applicable documentation submitted |  |  |  |  | Date | TRUE
Task Grouping | Billing/1099-R
Task | Fees | 101 | 1 | Distribution Specialist | FALSE | [5 empty] | Distribution
Task Item | Is distribution work billable? |  |  |  |  | Yes/No | TRUE
Task Item | If billable, enter fee amount |  |  |  |  | Text | FALSE
Task Item | Send fee information to accounting |  |  |  |  | Date | FALSE
Task | 1099-R Preparation | 101 | 0 | Distribution Specialist | FALSE | [5 empty] | Distribution
Task Item | Created 1099-R, if internally responsible |  |  |  |  | Waiting/NA/Completed | TRUE