## Template
Level | Name | Description | Project Type | Project Manager | Extension | Ext Deadline Increment | Ext Deadline Amount | Ext Static Deadline | Is Extendable | Project Frequency | Web Collection | Priority | Is Month End | Start Date Increment | Start Date Amount | Start Static Date
Project | 401(k) Annual Administration | Standard annual administration project template | Annual Administration | Administrator | FALSE | M | 7 |  | TRUE | Annual | TRUE | Normal | FALSE | M | 12
Level | Name\Question | Time Code | Days To Complete | Role Assigned | Review Step | DataType | Required | Project Field | Show on Project | Show on Plan | Worktray | Event | Task Category
Task Grouping | Data Collection
Task | Census Request Sent | 999 | 15 | Administrator | FALSE | [5 empty] | Unassigned
Task Item | An electronic Data Collection email needs to be sent to the client alerting them that the process for collecting their information using PlanSponsorLink.com is available. This process can be done using the Blast Email tools under the Communication menu. You can also manually send an email to alert the client. |  |  |  |  | None | FALSE
Task | Company Contact | 999 | 0 | Unassigned | FALSE | [5 empty] | Unassigned
Task Item | This task will be completed by your client using PlanSponsorLink.com. When they have completed and approved the data for this Task, the Task will show as completed here and on the Task Grouping tab. To see the details of the information your client has entered/approved, click on the Data Collection button on the header bar. |  |  |  |  | None | FALSE
Task | Company Data | 999 | 0 | Unassigned | FALSE | [5 empty] | Unassigned
Task Item | This task will be completed by your client using PlanSponsorLink.com. When they have completed and approved the data for this Task, the Task will show as completed here and on the Task Grouping tab. To see the details of the information your client has entered/approved, click on the Data Collection button on the header bar. |  |  |  |  | None | FALSE
Task | Principals | 999 | 0 | Unassigned | FALSE | [5 empty] | Unassigned
Task Item | This task will be completed by your client using PlanSponsorLink.com. When they have completed and approved the data for this Task, the Task will show as completed here and on the Task Grouping tab. To see the details of the information your client has entered/approved, click on the Data Collection button on the header bar. |  |  |  |  | None | FALSE
Task | Family Relationships | 999 | 0 | Unassigned | FALSE | [5 empty] | Unassigned
Task Item | This task will be completed by your client using PlanSponsorLink.com. When they have completed and approved the data for this Task, the Task will show as completed here and on the Task Grouping tab. To see the details of the information your client has entered/approved, click on the Data Collection button on the header bar. |  |  |  |  | None | FALSE
Task | Other Companies owned | 999 | 0 | Unassigned | FALSE | [5 empty] | Unassigned
Task Item | This task will be completed by your client using PlanSponsorLink.com. When they have completed and approved the data for this Task, the Task will show as completed here and on the Task Grouping tab. To see the details of the information your client has entered/approved, click on the Data Collection button on the header bar. |  |  |  |  | None | FALSE
Task | Contacts | 999 | 0 | Unassigned | FALSE | [5 empty] | Unassigned
Task Item | This task will be completed by your client using PlanSponsorLink.com. When they have completed and approved the data for this Task, the Task will show as completed here and on the Task Grouping tab. To see the issues your client has entered regarding the contacts listed, click on the Data Collection tab for this project. |  |  |  |  | None | FALSE
Task | Employer Questionnaire | 999 | 0 | Unassigned | FALSE | [5 empty] | Unassigned
Task Item | <strong>General Questionnaire</strong> |  |  |  |  | None | FALSE
Task Item | Do you deposit employee salary deferrals and loan repayments each pay period? |  |  |  |  | Yes/No | TRUE
Task Item | Will a request for extension of time for filing the company’s income tax return be made for this year? |  |  |  |  | Yes/No | TRUE
Task Item | Is the Employer part of a “Controlled Group” or an “Affiliated Service Group (ASG)”? |  |  |  |  | Yes/No | TRUE
Task Item | <strong>Employee Questions</strong> |  |  |  |  | None | FALSE
Task Item | Please indicate the last pay date for Employee Salary Deferrals that occurred during the plan year |  |  |  |  | Date | TRUE
Task Item | What was the dollar amount of the Employee Salary Deferral deposit associated with the last pay date in the question above? |  |  |  |  | Currency | TRUE
Task Item | Have you submitted copies of all asset statements for the plan year requested? |  |  |  |  | Yes/No | TRUE
Task | 5500 Questionnaire | 999 | 0 | Unassigned | FALSE | [5 empty] | Unassigned
Task Item | Did the employer fail to transmit to the plan any participant contributions (salary deferrals or loan payments) within the time period described in 29 CFR 2510.3-102? |  |  |  |  | Yes/No | TRUE
Task Item | Is the plan covered by a Fidelity Bond? |  |  |  |  | Yes/No | TRUE
Task Item | Yes, please enter the Fidelity Bond amount. If No, [ADD WEBSITE LINK HERE](Click here) to purchase coverage for your plan, then enter the amount once coverage has been set up. |  |  |  |  | Text | TRUE
Task Item | Enter Expiration Date of Fidelity Bond |  |  |  |  | Date | TRUE
Task Item | For plans that allow participant direction of investments, did the plan incur a Blackout period during the plan year? |  |  |  |  | Yes/No | TRUE
Task Item | Sent fidelity bond document to TPA. |  |  |  |  | Yes/No | TRUE
Task | Employee Census | 999 | 0 | Unassigned | FALSE | [5 empty] | Unassigned
Task Item | This task will be completed by your client using PlanSponsorLink.com. When they have completed and approved the data for this Task, the Task will show as completed here and on the Task Grouping tab. To see the details of the information your client has entered/approved, click on the Data Collection button on the header bar. |  |  |  |  | None | FALSE
Task | Final Approval | 999 | 0 | Unassigned | FALSE | [5 empty] | Unassigned
Task Item | This task will be completed by your client using PlanSponsorLink.com. When they have completed and approved the data for this Task, the Task will show as completed here and on the Task Grouping tab. To see the details of the information your client has entered/approved, click on the Data Collection button on the header bar. |  |  |  |  | None | FALSE
Task Grouping | Preliminary Review
Task | Census Review | 999 | 10 | Administrator | FALSE | [5 empty] | Unassigned
Task Item | Complete Census Review |  |  |  |  | Yes/No | TRUE
Task Item | How many follow-ups were necessary to get back completed data? |  |  |  |  | Integer | TRUE
Task Item | Date the Census was submitted, complete without any errors |  |  |  |  | Date | TRUE
Task | Second Check | 999 | 1 | Administrator | TRUE | [5 empty] | Unassigned
Task Item | Complete? |  |  |  |  | Yes/No | TRUE
Task Grouping | Eligibility Determination and Testing
Task | Eligibility Determination | 999 | 2 | Administrator | FALSE | [5 empty] | Unassigned
Task Item | Eligibility Determination |  |  |  |  | None | FALSE
Task Item | Complete eligibility determination |  |  |  |  | Checkbox | TRUE
Task Item | Enter the Plans Year End Participant Count |  |  |  |  | Integer | TRUE
Task Item | Enter the Assets at the end of the Year |  |  |  |  | Currency | TRUE
Task Item | Did the ownership group max out the DC limit? |  |  |  |  | Yes/No | TRUE
Task Item | Enter the percentage contribution to the staff |  |  |  |  | Integer | TRUE
Task Item | Enter any appropriate comments in the Notes tab. |  |  |  |  | None | FALSE
Task | ADP/ACP Test | 999 | 5 | Administrator | FALSE | [5 empty] | Unassigned
Task Item | Complete ADP/ACP testing |  |  |  |  | Checkbox | TRUE
Task Item | Did testing initially pass or fail? |  |  |  |  | Text | TRUE
Task Item | Correction method? |  |  |  |  | Text | TRUE
Task Item | Correction Method Explanation |  |  |  |  | Text | TRUE
Task Item | What percentage is the plan top heavy? |  |  |  |  | Text | TRUE
Task Item | Top Heavy results? |  |  |  |  | Text | TRUE
Task Item | Enter any appropriate comments in the Notes tab. |  |  |  |  | Text | FALSE
Task Item | 410(b) Test Results |  |  |  |  | Text | TRUE
Task Item | 402(g) Test Results |  |  |  |  | Text | TRUE
Task | Review of Eligibility, ADP/ACP testing | 999 | 0 | Administrator | TRUE | [5 empty] | Unassigned
Task Item | Review eligibility |  |  |  |  | Checkbox | TRUE
Task Item | Review ADP/ACP |  |  |  |  | Checkbox | TRUE
Task Item | Enter any appropriate comments in the Notes tab. |  |  |  |  | None | FALSE
Task Grouping | Contribution Calculations and Delivery
Task | Contribution calculations | 999 | 5 | Administrator | FALSE | [5 empty] | Unassigned
Task Item | Complete contribution calculations |  |  |  |  | Checkbox | TRUE
Task Item | Enter any appropriate comments in the Notes tab |  |  |  |  | None | FALSE
Task | Review - Contributions | 999 | 3 | Administrator | TRUE | [5 empty] | Unassigned
Task Item | Review contribution calculations |  |  |  |  | Checkbox | TRUE
Task Item | Enter any appropriate comments in the Notes tab |  |  |  |  | None | FALSE
Task | Compliance Report Delivery | 999 | 2 | Administrator | FALSE | [5 empty] | Unassigned
Task Item | Send compliance report to client through PlanSponsorLink.com |  |  |  |  | Checkbox | TRUE
Task Item | Enter any appropriate comments in the Notes tab |  |  |  |  | None | FALSE
Task Grouping | Annual Valuation and Forms Preparation
Task | Annual Valuation Preparation | 999 | 1 | Administrator | FALSE | [5 empty] | Unassigned
Task Item | Prepare annual valuation |  |  |  |  | Checkbox | TRUE
Task Item | Enter any appropriate comments in the Notes tab |  |  |  |  | None | FALSE
Task | Forms Completion | 999 | 2 | Administrator | FALSE | [5 empty] | Unassigned
Task Item | Complete appropriate government forms |  |  |  |  | Checkbox | TRUE
Task Item | Enter any appropriate comments in the Notes tab |  |  |  |  | None | FALSE
Task | Review - Annual Valuation and Forms | 999 | 2 | Administrator | TRUE | [5 empty] | Unassigned
Task Item | Review valuation and forms |  |  |  |  | Checkbox | TRUE
Task Item | Enter any appropriate comments in the Notes tab |  |  |  |  | None | FALSE
Task Grouping | Report Delivery
Task | Preparation of Annual Report | 999 | 1 | Administrator | FALSE | [5 empty] | Unassigned
Task Item | Prepare annual valuation for delivery to client |  |  |  |  | Checkbox | TRUE
Task Item | Complete Annual Valuation Cover letter |  |  |  |  | Checkbox | TRUE
Task Item | Enter any appropriate comments in the Notes tab |  |  |  |  | None | FALSE
Task | Billing Review | 999 | 0 | Administrator | TRUE | [5 empty] | Unassigned
Task Item | Review time and billing |  |  |  |  | Checkbox | TRUE
Task | Review - Annual Report and Billing | 999 | 3 | Administrator | TRUE | [5 empty] | Unassigned
Task Item | Review final report package |  |  |  |  | Checkbox | TRUE
Task Item | Send approved report and bill to client and copy all appropriate parties |  |  |  |  | Checkbox | TRUE
Task Item | Enter any appropriate comments in the Notes tab |  |  |  |  | None | FALSE
Task | EFAST Filing | 999 | 1 | Administrator | FALSE | [5 empty] | Unassigned
Task Item | EFAST Viewed |  |  |  |  | Date | TRUE
Task Item | EFAST Filed |  |  |  |  | Date | TRUE
Task Item | Enter any appropriate comments in the Notes tab |  |  |  |  | None | FALSE