## Template
Level | Name | Description | Project Type | Project Manager | Extension | Ext Deadline Increment | Ext Deadline Amount | Ext Static Deadline | Is Extendable | Project Frequency | Web Collection | Priority | Is Month End | Start Date Increment | Start Date Amount | Start Static Date
Project | 5558 Extension Filing |  | Extension | Administrator | TRUE | None |  |  | FALSE | Non-Recurring | FALSE | Normal | FALSE | None | 0
Level | Name\Question | Time Code | Days To Complete | Role Assigned | Review Step | DataType | Required | Project Field | Show on Project | Show on Plan | Worktray | Event | Task Category
Task Grouping | 5558 Preparation
Task | Client Notification | 101 | 3 | Administrator | FALSE | [5 empty] | Unassigned
Task Item | Send correspondence to client to notify them of the extension |  |  |  |  | Checkbox | TRUE
Task | Prepare 5558 and file on EFAST system | 101 | 1 | Admin Support | FALSE | [5 empty] | Unassigned
Task Item | Prepare 5558 and save under client directory |  |  |  |  | Checkbox | TRUE
Task Item | Enter date 5558 was filed on EFAST system |  |  |  |  | Date | TRUE | 5558 Filed | TRUE | FALSE
Task | Verification of extension | 101 | 1 | Administrator | TRUE | [5 empty] | Unassigned
Task Item | Confirm 5558 filing |  |  |  |  | Checkbox | TRUE
Task Item | Modify External Deadline on Annual Administration project Summary tab to new filing deadline date |  |  |  |  | Checkbox | TRUE
Task | Billing review | 101 | 2 | Billing Specialist | FALSE | [5 empty] | Unassigned
Task Item | Create invoice for extension and send to client |  |  |  |  | Checkbox | TRUE